## Hi Lvl WBS (hidden)
WBS # | TASKS
1.0 | Engine Mount Assembly
1.1 | Locate engine mount parts
1.2 | Laying mout to ruler
1.3 | Marking mount
1.4 | Cutting mount
1.5 | Inserting hook
1.6 | Testing adapter ring
1.7 | Glue & Dry
2.0 | Shock Cord Mount Assembly
2.1 | Locate cord mount parts
2.2 | Cut cord mount
2.3 | Crease assembly
2.4 | Glue mount assembly
2.5 | Fold mount assembly
2.6 | Clamp mount assembly
3.0 | Fin Preparation
3.1 | Select fin pattern
3.2 | Trace fin patterns
3.3 | Cut fin patterns
3.4 | Save scrap
3.5 | Course sand fins
3.6 | Fine sand fins
4.0 | Engine Mount Installation
4.1 | Locate body tube
4.2 | Measure body tube
4.3 | Spread glue
4.4 | Insert engine mount
5.0 | Tube Marking Detail
5.1 | Locate tube marking guide
5.2 | Wrap guide
5.3 | Mark tube
5.4 | Draw fin markings
6.0 | Fin Attachment
6.1 | Apply glue
6.2 | Apply second layer glue
6.3 | Adjust fin
6.4 | Set aside to dry
7.0 | Launch Lug Attachment
7.1 | Measure lug attachement
7.2 | Glue lug attachment
7.3 | Dry lug attachment
8.0 | Glue Reinforcement
8.1 | Reinforce fins
8.2 | Glue dry
9.0 | Shock Cord Mount Attachment
9.1 | Measure body tube
9.2 | Apply glue
9.3 | Set mount
9.4 | Set glue
10.0 | Parachute Assembly
10.1 | Cut out parachute
10.2 | Tape removal
10.3 | Tape attachment
10.4 | Shroud line assembly
10.5 | Shroud line attachment
11.0 | Parachute & Shock Cord Attachment to Nose Cone
11.1 | Shroud line threading
11.2 | Parachute pass throough
11.3 | Line tightening
11.4 | Shock cord tie down
12.0 | Finishing Rocket
12.1 | Verify dryness
12.2 | Prime rocket
12.3 | Paint rocket
12.4 | Decal rocket
12.5 | Decal qualitry assurance
12.6 | Large decals

## Activity List (hidden)
DELIVERABLES & TASKS | ACTIVITIES
Engine Mount Assembly
Locate engine mount parts
Locate light blue engine mount tube
Locate engine hook
Locate green adapter ring
Laying mount to ruler
Move tube to ruler
Align with zero mark
Marking mount
Take pencil
Mark tube
Mark 25mm
Mark 64 mm
Cutting mount
Cut 3mm slit
Inserting hook
Insert hook
Extend hook
Testing adapter ring
Slide ring into front of engine tube
Slide ring over engine hook to 25mm mark
Glue & Dry
Apply glue
Apply glue to one side
Apply glue to other side
Dry glue
Set assembly aside
Allow to dry
Shock Cord Mount Assembly
Locate cord mount parts
Locate cord mount on pattern sheet
Cut cord mount
Cut cord mount along outline
Crease assembly
Fold on dotted lines
Crease on dotted lines
Glue mount assembly
Spread glue
Lay end of shock cord in glue
Fold mount assembly
Fold section 1
Apply glue section 3
Fold again
Clamp mount assembly
Clamp assembly
Allow to dry
Fin Preparation
Select fin pattern
Select fin pattern
Cut fin pattern from sheet
Trace fin patterns
Trace fin #1
Match fin #1
Trace fin #2
Match fin #2
Trace fin #2
Match fin #2
Cut fin patterns
Cut fin #1
Chect fin #1
Cut fin #2
Chect fin #2
Cut fin #3
Chect fin #3
Save scrap
Set aside piece scrap basa wood
Course sand fins
Lay sandpaper
Stack fins
Sand fins
Fine sand fins
Fine sand fin #1
Round leading edge fin #1
Round trailing edge fin #1
Streamline training edge fin #1
Fine sand fin #2
Round leading edge fin #2
Round trailing edge fin #2
Streamline training edge fin #2
Fine sand fin #3
Round leading edge fin #3
Round trailing edge fin #3
Streamline training edge fin #3
Engine Mount Installation
Locate body tube
Locate body tube
Measure body tube
Measure body tube 38 mm
Spread glue
Spread glue around body tube
Insert engine mount
Insert engine mount assembly into body tube
Tube Marking Detail
Locate tube marking guide
Locate tube marking guide on pattern sheet
Cut guide alone outline
Wrap guide
Wrap guide around body tube
Tape guide to body tube
Mark tube
Mark tube for fins
Mark tube for fin #1
Mark tube for fin #2
Mark tube for fin #3
Write LL on body tube
Remove guide
Draw fin markings
Fin #1
Draw straight line
Extend line 76mm
Fin #2
Draw straight line
Extend line 76mm
Fin #3
Draw straight line
Extend line 76mm
Draw launch lug line
Draw line 102 mm
Fin Attachment
Apply glue to root edges of fins
Apply to fin #1
Allow fin #1 to dry
Apply to fin #2
Allow fin #2 to dry
Apply to fin #3
Allow fin #3 to dry
Apply second layer glue
Apply more glue to Fin #1
Set fin #1
Press fin #1
Apply more glue to Fin #2
Set fin #2
Press fin #2
Apply more glue to Fin #3
Set fin #3
Press fin #3
Adjust fins
Adjust fin #1
Attach fin #1
Adjust fin #2
Attach fin #2
Adjust fin #3
Attach fin #3
Set aside to dry
Stand rocket on drying table
Allow fins to dry
Launch Lug Attachment
Measure lug attachement
Measure 41mm
Mark attachment point
Glue lug attachment
Apply glue to launch lug
Attach launch lug to body tube
Dry lug attachment
Ensure launch lug alignment
Allow to dry
Glue Reinforcement
Reinforce fins
Reinforce fin fin #1
Reinforce fin fin #2
Reinforce fin fin #3
Reinforce launch lug
Reinforch side 1
Reinforce side 2
Glue drying
Stand rocket on drying table
Wipe away excess glue
Allow to dry
Shock Cord Mount Attachment
Measure body tube
Measure 25mm
Apply glue
Apply glue to shock cord
Insert cord into tube
Set mount
Set mount 25mm
Press mount into glue
Set glue
Hold mount attachment
Allow to dry
Parachute Assembly
Cut out parachute
Cut parachute along line
Tape removal
Remove tape
Fold shroud lines
Cut shroud lines
Tape attachment
Attach tape rings
Attach tape ring #1
Attach tape ring #2
Attach tape ring #3
Attach tape ring #4
Attach tape ring #5
Attach tape ring #6
Press tape tape rings into place
Press tape tape rings into place #1
Press tape tape rings into place #2
Press tape tape rings into place #3
Press tape tape rings into place #4
Press tape tape rings into place #5
Press tape tape rings into place #6
Punch tape ring holes
Punch tape ring holes #1
Punch tape ring holes #2
Punch tape ring holes #3
Punch tape ring holes #4
Punch tape ring holes #5
Punch tape ring holes #6
Shroud line assembly
Pass shroud line through hole
Tie lines together
Parachute & Shock Cord Attachment to Nose Cone
Shroud line threading
Thread shroud lines
Parachute pass throough
Pass parachute through loop
Line tightening
Pull lines tight
Shock cord tie down
Tie down shock cord free end
Finishing Rocket
Verify dryness
Check to ensure glue joint are dry
Prime rocket
Apply primer coat #1
Sand rocket body #1
Apply primer coat #2
Sand rocket body #2
Paint rocket
Insert paint handle
Apply paint to rocket
Allow to dry
Apply Water Decals
Cut decals
Decal #1
Decal #2
Decal #3
Decal #4
Decal #5
Decal #6
Decal #7
Decal #8
Decal #9
Decal #10
Decal #11
Decal #12
Decal #13
Dip in water
Decal #1
Decal #2
Decal #3
Decal #4
Decal #5
Decal #6
Decal #7
Decal #8
Decal #9
Decal #10
Decal #11
Decal #12
Decal #13
Slip decals
Decal #1
Decal #2
Decal #3
Decal #4
Decal #5
Decal #6
Decal #7
Decal #8
Decal #9
Decal #10
Decal #11
Decal #12
Decal #13
Blot decals
Decal #1
Decal #2
Decal #3
Decal #4
Decal #5
Decal #6
Decal #7
Decal #8
Decal #9
Decal #10
Decal #11
Decal #12
Decal #13
Dry decals
Allow to dry overnight
Apply clear spray to decals
Apply spray to rocket
Apply large decals
Peel backing
Cut away backing
Align decal
Peel off backing
Smooth decal

## WBS (hidden)
WBS # | TASKS
1.0 | Engine Mount Assembly
1.1 | Locate engine mount parts
1.1.1 | Locate light blue engine mount tube
1.1.2 | Locate engine hook
1.1.3 | Locate green adapter ring
1.2 | Laying mount to ruler
1.2.1 | Move tube to ruler
1.2.2 | Align with zero mark
1.3 | Marking mount
1.3.1 | Take pencil
1.3.2 | Mark tube
1.3.2.1 | Mark 25mm
1.3.2.2 | Mark 64 mm
1.4 | Cutting mount
1.4.1 | Cut 3mm slit
1.5 | Inserting hook
1.5.1 | Insert hook
1.5.2 | Extend hook
1.6 | Testing adapter ring
1.6.1 | Slide ring into front of engine tube
1.6.2 | Slide ring over engine hook to 25mm mark
1.7 | Glue & Dry
1.7.1 | Apply glue
1.7.1.1 | Apply glue to one side
1.7.1.2 | Apply glue to other side
1.7.2 | Dry glue
1.7.2.1 | Set assembly aside
1.7.2.2 | Allow to dry
2.0 | Shock Cord Mount Assembly
2.1 | Locate cord mount parts
2.1.1 | Locate cord mount on pattern sheet
2.2 | Cut cord mount
2.2.1 | Cut cord mount along outline
2.3 | Crease assembly
2.3.1 | Fold on dotted lines
2.3.2 | Crease on dotted lines
2.4 | Glue mount assembly
2.4.1 | Spread glue
2.4.2 | Lay end of shock cord in glue
2.5 | Fold mount assembly
2.5.1 | Fold section 1
2.5.2 | Apply glue section 3
2.5.3 | Fold again
2.6 | Clamp mount assembly
2.6.1 | Clamp assembly
2.6.2 | Allow to dry
3.0 | Fin Preparation
3.1 | Select fin pattern
3.1.1 | Select fin pattern
3.1.2 | Cut fin pattern from sheet
3.2 | Trace fin patterns
3.2.1 | Trace fin #1
3.2.2 | Match fin #1
3.2.3 | Trace fin #2
3.2.4 | Match fin #2
3.2.5 | Trace fin #2
3.2.6 | Match fin #2
3.3 | Cut fin patterns
3.3.1 | Cut fin #1
3.3.2 | Chect fin #1
3.3.3 | Cut fin #2
3.3.4 | Chect fin #2
3.3.5 | Cut fin #3
3.3.6 | Chect fin #3
3.4 | Save scrap
3.4.1 | Set aside piece scrap basa wood
3.5 | Course sand fins
3.5.1 | Lay sandpaper
3.5.2 | Stack fins
3.5.3 | Sand fins
3.6 | Fine sand fins
3.6.1 | Fine sand fin #1
3.6.1.1 | Round leading edge fin #1
3.6.1.2 | Round trailing edge fin #1
3.6.1.3 | Streamline training edge fin #1
3.6.2 | Fine sand fin #2
3.6.2.1 | Round leading edge fin #2
3.6.2.2 | Round trailing edge fin #2
3.6.2.3 | Streamline training edge fin #2
3.6.3 | Fine sand fin #3
3.6.3.1 | Round leading edge fin #3
3.6.3.2 | Round trailing edge fin #3
3.6.3.3 | Streamline training edge fin #3
4.0 | Engine Mount Installation
4.1 | Locate body tube
4.1.1 | Locate body tube
4.2 | Measure body tube
4.2.1 | Measure body tube 38 mm
4.3 | Spread glue
4.3.1 | Spread glue around body tube
4.4 | Insert engine mount
4.4.1 | Insert engine mount assembly into body tube
5.0 | Tube Marking Detail
5.1 | Locate tube marking guide
5.1.1 | Locate tube marking guide on pattern sheet
5.1.2 | Cut guide alone outline
5.2 | Wrap guide
5.2.1 | Wrap guide around body tube
5.2.2 | Tape guide to body tube
5.3 | Mark tube
5.3.1 | Mark tube for fins
5.3.1.1 | Mark tube for fin #1
5.3.1.2 | Mark tube for fin #2
5.3.1.3 | Mark tube for fin #3
5.3.2 | Write LL on body tube
5.3.3 | Remove guide
5.4 | Draw fin markings
5.4.1 | Fin #1
5.4.1.1 | Draw straight line
5.4.1.2 | Extend line 76mm
5.4.2 | Fin #2
5.4.2.1 | Draw straight line
5.4.2.2 | Extend line 76mm
5.4.3 | Fin #3
5.4.3.1 | Draw straight line
5.4.3.2 | Extend line 76mm
5.4.4 | Draw launch lug line
5.4.4.1 | Draw line 102 mm
6.0 | Fin Attachment
6.1 | Apply glue to root edges of fins
6.1.1 | Apply to fin #1
6.1.2 | Allow fin #1 to dry
6.1.3 | Apply to fin #2
6.1.4 | Allow fin #2 to dry
6.1.5 | Apply to fin #3
6.1.6 | Allow fin #3 to dry
6.2 | Apply second layer glue
6.2.1 | Apply more glue to Fin #1
6.2.2 | Set fin #1
6.2.3 | Press fin #1
6.2.4 | Apply more glue to Fin #2
6.2.5 | Set fin #2
6.2.6 | Press fin #2
6.2.7 | Apply more glue to Fin #3
6.2.8 | Set fin #3
6.2.9 | Press fin #3
6.3 | Adjust fins
6.3.1 | Adjust fin #1
6.3.2 | Attach fin #1
6.3.3 | Adjust fin #2
6.3.4 | Attach fin #2
6.3.5 | Adjust fin #3
6.3.6 | Attach fin #3
6.4 | Set aside to dry
6.4.1 | Stand rocket on drying table
6.4.2 | Allow fins to dry
7.0 | Launch Lug Attachment
7.1 | Measure lug attachement
7.1.1 | Measure 41mm
7.1.2 | Mark attachment point
7.2 | Glue lug attachment
7.2.1 | Apply glue to launch lug
7.2.2 | Attach launch lug to body tube
7.3 | Dry lug attachment
7.3.1 | Ensure launch lug alignment
7.3.2 | Allow to dry
8.0 | Glue Reinforcement
8.1 | Reinforce fins
8.1.1 | Reinforce fin fin #1
8.1.2 | Reinforce fin fin #2
8.1.3 | Reinforce fin fin #3
8.2 | Reinforce launch lug
8.2.1 | Reinforch side 1
8.2.2 | Reinforce side 2
8.2 | Glue drying
8.2.1 | Stand rocket on drying table
8.2.2 | Wipe away excess glue
8.2.3 | Allow to dry
9.0 | Shock Cord Mount Attachment
9.1 | Measure body tube
9.1.1 | Measure 25mm
9.2 | Apply glue
9.2.1 | Apply glue to shock cord
9.2.2 | Insert cord into tube
9.3 | Set mount
9.3.1 | Set mount 25mm
9.3.2 | Press mount into glue
9.4 | Set glue
9.4.1 | Hold mount attachment
9.4.2 | Allow to dry
10.0 | Parachute Assembly
10.1 | Cut out parachute
10.1.1 | Cut parachute along line
10.2 | Tape removal
10.2.1 | Remove tape
10.2.2 | Fold shroud lines
10.2.3 | Cut shroud lines
10.3 | Tape attachment
10.3.1 | Attach tape rings
10.3.1.1 | Attach tape ring #1
10.3.1.2 | Attach tape ring #2
10.3.1.3 | Attach tape ring #3
10.3.1.4 | Attach tape ring #4
10.3.1.5 | Attach tape ring #5
10.3.1.6 | Attach tape ring #6
10.3.2 | Press tape tape rings into place
10.3.2.1 | Press tape tape rings into place #1
10.3.2.2 | Press tape tape rings into place #2
10.3.2.3 | Press tape tape rings into place #3
10.3.2.4 | Press tape tape rings into place #4
10.3.2.5 | Press tape tape rings into place #5
10.3.2.6 | Press tape tape rings into place #6
10.3.3 | Punch tape ring holes
10.3.3.1 | Punch tape ring holes #1
10.3.3.2 | Punch tape ring holes #2
10.3.3.3 | Punch tape ring holes #3
10.3.3.4 | Punch tape ring holes #4
10.3.3.5 | Punch tape ring holes #5
10.3.3.6 | Punch tape ring holes #6
10.4 | Shroud line assembly
10.4.1 | Pass shroud line through hole
10.4.2 | Tie lines together
11.0 | Parachute & Shock Cord Attachment to Nose Cone
11.1 | Shroud line threading
11.1.1 | Thread shroud lines
11.2 | Parachute pass throough
11.2.1 | Pass parachute through loop
11.3 | Line tightening
11.3.1 | Pull lines tight
11.4 | Shock cord tie down
11.4.1 | Tie down shock cord free end
12.0 | Finishing Rocket
12.1 | Verify dryness
12.1.1 | Check to ensure glue joint are dry
12.2 | Prime rocket
12.2.1 | Apply primer coat #1
12.2.2 | Sand rocket body #1
12.2.3 | Apply primer coat #2
12.2.4 | Sand rocket body #2
12.3 | Paint rocket
12.3.1 | Insert paint handle
12.3.2 | Apply paint to rocket
12.3.3 | Allow to dry
12.4 | Apply Water Decals
12.4.1 | Cut decals
12.4.1.1 | Decal #1
12.4.1.2 | Decal #2
12.4.1.3 | Decal #3
12.4.1.4 | Decal #4
12.4.1.5 | Decal #5
12.4.1.6 | Decal #6
12.4.1.7 | Decal #7
12.4.1.8 | Decal #8
12.4.1.9 | Decal #9
12.4.1.10 | Decal #10
12.4.1.11 | Decal #11
12.4.1.12 | Decal #12
12.4.1.13 | Decal #13
12.4.2 | Dip in water
12.4.2.1 | Decal #1
12.4.2.2 | Decal #2
12.4.2.3 | Decal #3
12.4.2.4 | Decal #4
12.4.2.5 | Decal #5
12.4.2.6 | Decal #6
12.4.2.7 | Decal #7
12.4.2.8 | Decal #8
12.4.2.9 | Decal #9
12.4.2.10 | Decal #10
12.4.2.11 | Decal #11
12.4.2.12 | Decal #12
12.4.2.13 | Decal #13
12.4.3 | Slip decals
12.4.3.1 | Decal #1
12.4.3.2 | Decal #2
12.4.3.3 | Decal #3
12.4.3.4 | Decal #4
12.4.3.5 | Decal #5
12.4.3.6 | Decal #6
12.4.3.7 | Decal #7
12.4.3.8 | Decal #8
12.4.3.9 | Decal #9
12.4.3.10 | Decal #10
12.4.3.11 | Decal #11
12.4.3.12 | Decal #12
12.4.3.13 | Decal #13
12.4.4 | Blot decals
12.4.4.1 | Decal #1
12.4.4.2 | Decal #2
12.4.4.3 | Decal #3
12.4.4.4 | Decal #4
12.4.4.5 | Decal #5
12.4.4.6 | Decal #6
12.4.4.7 | Decal #7
12.4.4.8 | Decal #8
12.4.4.9 | Decal #9
12.4.4.10 | Decal #10
12.4.4.11 | Decal #11
12.4.4.12 | Decal #12
12.4.4.13 | Decal #13
12.4.5 | Dry decals
12.5.1 | Allow to dry overnight
12.4.6 | Apply clear spray to decals
12.4.1 | Apply spray to rocket
12.5 | Apply large decals
12.5.1 | Peel backing
12.5.2 | Cut away backing
12.5.3 | Align decal
12.5.4 | Peel off backing
12.5.5 | Smooth decal

## Network (hidden)
Engine Mount Assembly | Engine Mount Installation |  |  | Launch Lug Attachment
Fin Preparation |  | Tube Marking Detail | Fin Attachment |  | Glue Reinforcement
Shock Cord Mount Assembly | [5 empty] | Finishing Rocket
| Parachute & Shock Cord Attachment to Nose Cone | Shock Cord Mount Attachment
Parachute Assembly

## Gantt
Enter Your WBS Level 1 Work Packages Here
|  | Week 1 | [7 empty] | Week 2 | [7 empty] | Week 3 | [7 empty] | Week 4 | [7 empty] | Week 5 | [7 empty] | Week 6 | [7 empty] | Week 7 | [7 empty] | Week 8 | [7 empty] | Week 9 | [7 empty] | Week 10 | [7 empty] | Week 11 | [7 empty] | Week 12 | [7 empty] | Week 13 | [7 empty] | Week 14 | [7 empty] | Week 15 | [7 empty] | Week 16 | [7 empty] | Week 17 | [7 empty] | Week 18 | [7 empty] | Week 19 |  |  | Doesn't End
WBS # | TASKS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147
1.0 | Initiation
2.0 | Planning
3.0 | Execution
4.0 | Monitoring/Controlling
5.0 | Closing

## Duration Est
Enter Your WBS Here and remove example below |  | Fill in your time and cost estimates here. Total for each work package and for the project
WBS # | TASKS | Duration | Start Date | End Date | Labor | Materials | Fees | Other
1.0 | Initiation |  | 2023-05-01 | 2023-05-12
1.1 | Brainstorm Idea |  | 2023-05-01 | 2023-05-01
1.1.1 | Plan Meeting |  | 2023-05-02 | 2023-05-03
1.1.2 | Make a Group Decision |  | 2023-05-04 | 2023-05-04
1.1.3 | Finialize the Decision |  | 2023-05-05 | 2023-05-09
1.2 | Project Meaning and Reason |  | 2023-05-08 | 2023-05-07
1.2.1 | Find the focus of Project |  | 2023-05-08 | 2023-05-09
1.2.1.1 | Find out Target audience |  | 2023-05-08 | 2023-05-09
1.2.2 | Why are we doing this? |  | 2023-05-08 | 2023-05-09
1.3 | Contact Stakeholder |  | 2023-05-10 | 2023-05-10
1.3.1 | Contact |  | 2023-05-10 | 2023-05-10
1.3.2 | Set Up Meeting Time |  | 2023-05-10 | 2023-05-10
1.4 | Present Project to Stakeholders |  | 2023-05-12 | 2023-05-12
1.4.1 | Show Them Our Objective |  | 2023-05-12 | 2023-05-12
| Finalize Decision |  | 2023-05-12 | 2023-05-12
2.0 | Planning |  | 2023-05-15 | 2023-07-03
2.1 | Establish the Budget for the Project |  | 2023-05-15 | 2023-05-20
2.1.1 | Determine resources |  | 2023-05-15 | 2023-05-20
2.2 | Determine Staff (Roles) |  | 2023-05-17 | 2023-06-26
2.2.1 | Put Applications Out For Staff |  | 2023-05-17 | 2023-05-31
2.2.2 | Look at Application |  | 2023-05-31 | 2023-06-07
2.2.3 | Hire Worker |  | 2023-06-08 | 2023-06-13
2.2.3.1 | Train Employees |  | 2023-06-15 | 2023-06-26
2.3 | Create Outline for Project |  | 2023-06-27 | 2023-06-27
2.3.1 | Identify Topic |  | 2023-06-27 | 2023-06-27
2.3.2 | Decide Point We Need To Make |  | 2023-06-27 | 2023-06-27
2.4 | Set Specific Goals |  | 2023-06-28 | 2023-06-29
2.5 | Create a Reasonable Timeframe |  | 2023-06-30 | 2023-07-03
2.5.1 | Meet with Team Members |  | 2023-06-30 | 2023-07-03
2.5.2 | Dicuss End Date Of Project |  | 2023-06-30 | 2023-07-03
2.5.3 | Come to a Decission |  | 2023-07-03 | 2023-07-03
3.0 | Execution |  | 2023-07-04 | 2023-08-22
3.1 | Plan Teams |  | 2023-07-04 | 2023-07-05
3.1.1 | Give Roles Out for Employees |  | 2023-07-04 | 2023-07-05
3.1.2 | Give Them Deadlines |  | 2023-07-04 | 2023-07-05
3.2 | Split up into different divisions |  | 2023-07-06 | 2023-07-06
3.2.1 | Developers |  | 2023-07-06 | 2023-07-06
3.2.2 | Host & Domain |  | 2023-07-06 | 2023-07-06
3.2.3 | Content Creators |  | 2023-07-06 | 2023-07-06
3.2.4 | Website Traffic |  | 2023-07-06 | 2023-07-06
3.3 | Have Meet Up With Separate Groups Within the Projet to Know How Everything is Running |  | 2023-07-13 | 2023-08-04
3.3.1 | Developers |  | 2023-07-13 | 2023-08-04
3.3.2 | Host & Domain |  | 2023-07-13 | 2023-07-27
3.3.3 | Content Creators |  | 2023-07-13 | 2023-08-04
3.3.4 | Website Traffic |  | 2023-07-13 | 2023-07-27
3.3.5 | Get Help Where it is needed |  | 2023-07-13 | 2023-08-04
3.3.5.1 | Provided them the needed resourses |  | 2023-07-13 | 2023-08-04
3.4 | Start Building Website |  | 2023-08-07 | 2023-08-22
3.4.1 | Web Design |  | 2023-08-07 | 2023-08-22
3.4.1.1. | Domain |  | 2023-08-07 | 2023-08-22
3.4.2 | Web Key |  | 2023-08-07 | 2023-08-22
3.4.3 | Develop |  | 2023-08-07 | 2023-08-22
3.5 | Keep Stakeholders Updated |  | 2023-08-14 | 2023-08-15
3.5.1 | Contact Them for meeting date |  | 2023-08-14 | 2023-08-15
3.5.2 | Update them on Project |  | 2023-08-14 | 2023-08-15
4.0 | Monitoring/Controlling |  | 2023-08-07 | 2023-09-02
4.1 | Contact each division to find out where their progress is |  | 2023-08-07 | 2023-08-25
4.1.1 | Developers |  | 2023-08-07 | 2023-08-25
4.1.2 | Host & Domain |  | 2023-08-07 | 2023-08-25
4.1.3. | Content Creators |  | 2023-08-07 | 2023-08-25
4.1.4 | Website Traffic |  | 2023-08-07 | 2023-08-25
4.1.5 | Provide Help If it is needed |  | 2023-08-07 | 2023-08-25
4.2 | Track Milestones |  | 2023-08-07 | 2023-08-25
4.2.1 | Keep track Of Progress |  | 2023-08-07 | 2023-08-25
4.3 | Update and/or modify the Project Schedule if Needed |  | 2023-08-21 | 2023-08-25
4.4 | Test Run(Check Performance)/ Check If Deliverables are met |  | 2023-08-25 | 2023-09-02
5.0 | Closing |  | 2023-09-02 | Doesn't End
5.1 | Address to Stakeholders Project is Ready |  | 2023-09-02 | 2023-09-04
5.1.1 | Contact them to set up Meeting |  | 2023-09-02 | 2023-09-02
5.1.2 | Give Them Intel about Project |  | 2023-09-03 | 2023-09-03
5.1.3 | Showcase Project to them |  | 2023-09-04 | 2023-09-04
5.2 | Set Release Dat |  | 2023-09-04 | 2023-09-04
5.2.1 | Dicuss with Team Leads |  | 2023-09-04 | 2023-09-04
5.2.2 | Agree on Relase Date |  | 2023-09-04 | 2023-09-04
5.3 | Publish The Website |  | 2023-09-06 | 2023-09-06
5.3.1 | Test one last time |  | 2023-09-06 | 2023-09-06
5.4 | Monitor Website |  | 2023-09-06 | Doesn't End
5.4.1 | Look for Comments/Feedback |  | 2023-09-06 | Doesn't End
5.4.1.1 | Take Comment/Feeback into Consideration |  | 2023-09-06 | Doesn't End
5.4.1.2 | Team Meeting on Comment/Feedback |  | 2023-09-06 | Doesn't End
5.4.1.3 | Come to an agree what to do |  | 2023-09-06 | Doesn't End
5.4.2 | Update Website |  | As Needed | Doesn't End
5.4.2.1 | Fix Bugs |  | As Needed | Doesn't End
5.4.2.2 | Keep it Fresh and Moderate |  | As Needed | Doesn't End
5.4.3 | Check Sercuity Often |  | Weekly | Doesn't End
5.4.3.1 | Run Scan |  | Weekly | Doesn't End

## X-Impact (hidden)
WBS # | TASKS | Fitter | Draftsman | Cutter | Gluer | Sander
1.0 | Engine Mount Assembly | X | X | X | X
2.0 | Shock Cord Mount Assembly | X |  | X | X
3.0 | Fin Preparation | X | X | X |  | X
4.0 | Engine Mount Installation | X | X |  | X
5.0 | Tube Marking Detail
6.0 | Fin Attachment
7.0 | Launch Lug Attachment
8.0 | Glue Reinforcement
9.0 | Shock Cord Mount Attachment
10.0 | Parachute Assembly
11.0 | Parachute & Shock Cord Attachment to Nose Cone
12.0 | Finishing Rocket

## RAM (hidden)
WBS # | TASKS | Fitter | Draftsman | Cutter | Gluer | Painter | Sander | Sr Sander | Dummy
1.0 | Engine Mount Assembly
1.1 | Locate engine mount parts
1.1.1 | Locate light blue engine mount tube
1.1.2 | Locate engine hook
1.1.3 | Locate green adapter ring
1.2 | Laying mount to ruler
1.2.1 | Move tube to ruler
1.2.2 | Align with zero mark
1.3 | Marking mount
1.3.1 | Take pencil
1.3.1.1 | Take pencil
1.3.2 | Mark tube
1.3.2.1 | Mark 25mm
1.3.2.2 | Mark 64 mm
1.4 | Cutting mount
1.4.1 | Cut 3mm slit
1.5 | Inserting hook
1.5.1 | Insert hook
1.5.2 | Extend hook
1.6 | Testing adapter ring
1.6.1 | Slide ring into front of engine tube
1.6.2 | Slide ring over engine hook to 25mm mark
1.7 | Glue & Dry
1.7.1 | Apply glue
1.7.1.1 | Apply glue to one side
1.7.1.2 | Apply glue to other side
1.7.2 | Dry glue
1.7.2.1 | Set assembly aside
1.7.2.2 | Allow to dry
2.0 | Shock Cord Mount Assembly
2.1 | Locate cord mount parts
2.1.1 | Locate cord mount on pattern sheet
2.2 | Cut cord mount
2.2.1 | Cut cord mount along outline
2.3 | Crease assembly
2.3.1 | Fold on dotted lines
2.3.2 | Crease on dotted lines
2.4 | Glue mount assembly
2.4.1 | Spread glue
2.4.2 | Lay end of shock cord in glue
2.5 | Fold mount assembly
2.5.1 | Fold section 1
2.5.2 | Apply glue section 3
2.5.3 | Fold again
2.6 | Clamp mount assembly
2.6.1 | Clamp assembly
2.6.2 | Allow to dry
3.0 | Fin Preparation
3.1 | Select fin pattern
3.1.1 | Select fin pattern
3.1.2 | Cut fin pattern from sheet
3.2 | Trace fin patterns
3.2.1 | Trace fin #1
3.2.2 | Match fin #1
3.2.3 | Trace fin #2
3.2.4 | Match fin #2
3.2.5 | Trace fin #2
3.2.6 | Match fin #2
3.3 | Cut fin patterns
3.3.1 | Cut fin #1
3.3.2 | Chect fin #1
3.3.3 | Cut fin #2
3.3.4 | Chect fin #2
3.3.5 | Cut fin #3
3.3.6 | Chect fin #3
3.4 | Save scrap
3.4.1 | Set aside piece scrap basa wood
3.5 | Course sand fins
3.5.1 | Lay sandpaper
3.5.2 | Stack fins
3.5.3 | Sand fins
3.6 | Fine sand fins
3.6.1 | Fine sand fin #1
3.6.1.1 | Round leading edge fin #1
3.6.1.2 | Round trailing edge fin #1
3.6.1.3 | Streamline training edge fin #1
3.6.2 | Fine sand fin #2
3.6.2.1 | Round leading edge fin #2
3.6.2.2 | Round trailing edge fin #2
3.6.2.3 | Streamline training edge fin #2
3.6.3 | Fine sand fin #3
3.6.3.1 | Round leading edge fin #3
3.6.3.2 | Round trailing edge fin #3
3.6.3.3 | Streamline training edge fin #3
4.0 | Engine Mount Installation
4.1 | Locate body tube
4.1.1 | Locate body tube
4.2 | Measure body tube
4.2.1 | Measure body tube 38 mm
4.3 | Spread glue
4.3.1 | Spread glue around body tube
4.4 | Insert engine mount
4.4.1 | Insert engine mount assembly into body tube
5.0 | Tube Marking Detail
5.1 | Locate tube marking guide
5.1.1 | Locate tube marking guide on pattern sheet
5.1.2 | Cut guide alone outline
5.2 | Wrap guide
5.2.1 | Wrap guide around body tube
5.2.2 | Tape guide to body tube
5.3 | Mark tube
5.3.1 | Mark tube for fins
5.3.1.1 | Mark tube for fin #1
5.3.1.2 | Mark tube for fin #2
5.3.1.3 | Mark tube for fin #3
5.3.2 | Write LL on body tube
5.3.3 | Remove guide
5.4 | Draw fin markings
5.4.1 | Fin #1
5.4.1.1 | Draw straight line
5.4.1.2 | Extend line 76mm
5.4.2 | Fin #2
5.4.2.1 | Draw straight line
5.4.2.2 | Extend line 76mm
5.4.3 | Fin #3
5.4.3.1 | Draw straight line
5.4.3.2 | Extend line 76mm
5.4.4 | Draw launch lug line
5.4.4.1 | Draw line 102 mm
6.0 | Fin Attachment
6.1 | Apply glue to root edges of fins
6.1.1 | Apply to fin #1
6.1.2 | Allow fin #1 to dry
6.1.3 | Apply to fin #2
6.1.4 | Allow fin #2 to dry
6.1.5 | Apply to fin #3
6.1.6 | Allow fin #3 to dry
6.2 | Apply second layer glue
6.2.1 | Apply more glue to Fin #1
6.2.2 | Set fin #1
6.2.3 | Press fin #1
6.2.4 | Apply more glue to Fin #2
6.2.5 | Set fin #2
6.2.6 | Press fin #2
6.2.7 | Apply more glue to Fin #3
6.2.8 | Set fin #3
6.2.9 | Press fin #3
6.3 | Adjust fins
6.3.1 | Adjust fin #1
6.3.2 | Attach fin #1
6.3.3 | Adjust fin #2
6.3.4 | Attach fin #2
6.3.5 | Adjust fin #3
6.3.6 | Attach fin #3
6.4 | Set aside to dry
6.4.1 | Stand rocket on drying table
6.4.2 | Allow fins to dry
7.0 | Launch Lug Attachment
7.1 | Measure lug attachement
7.1.1 | Measure 41mm
7.1.2 | Mark attachment point
7.2 | Glue lug attachment
7.2.1 | Apply glue to launch lug
7.2.2 | Attach launch lug to body tube
7.3 | Dry lug attachment
7.3.1 | Ensure launch lug alignment
7.3.2 | Allow to dry
8.0 | Glue Reinforcement
8.1 | Reinforce fins
8.1.1 | Reinforce fin fin #1
8.1.2 | Reinforce fin fin #2
8.1.3 | Reinforce fin fin #3
8.2 | Reinforce launch lug
8.2.1 | Reinforch side 1
8.2.2 | Reinforce side 2
8.3 | Glue drying
8.3.1 | Stand rocket on drying table
8.3.2 | Wipe away excess glue
8.3.3 | Allow to dry
9.0 | Shock Cord Mount Attachment
9.1 | Measure body tube
9.1.1 | Measure 25mm
9.2 | Apply glue
9.2.1 | Apply glue to shock cord
9.2.2 | Insert cord into tube
9.3 | Set mount
9.3.1 | Set mount 25mm
9.3.2 | Press mount into glue
9.4 | Set glue
9.4.1 | Hold mount attachment
9.4.2 | Allow to dry
10.0 | Parachute Assembly
10.1 | Cut out parachute
10.1.1 | Cut parachute along line
10.2 | Tape removal
10.2.1 | Remove tape
10.2.2 | Fold shroud lines
10.2.3 | Cut shroud lines
10.3 | Tape attachment
10.3.1 | Attach tape rings
10.3.1.1 | Attach tape ring #1
10.3.1.2 | Attach tape ring #2
10.3.1.3 | Attach tape ring #3
10.3.1.4 | Attach tape ring #4
10.3.1.5 | Attach tape ring #5
10.3.1.6 | Attach tape ring #6
10.3.2 | Press tape tape rings into place
10.3.2.1 | Press tape tape rings into place #1
10.3.2.2 | Press tape tape rings into place #2
10.3.2.3 | Press tape tape rings into place #3
10.3.2.4 | Press tape tape rings into place #4
10.3.2.5 | Press tape tape rings into place #5
10.3.2.6 | Press tape tape rings into place #6
10.3.3 | Punch tape ring holes
10.3.3.1 | Punch tape ring holes #1
10.3.3.2 | Punch tape ring holes #2
10.3.3.3 | Punch tape ring holes #3
10.3.3.4 | Punch tape ring holes #4
10.3.3.5 | Punch tape ring holes #5
10.3.3.6 | Punch tape ring holes #6
10.4 | Shroud line assembly
10.4.1 | Pass shroud line through hole
10.4.2 | Tie lines together
11.0 | Parachute & Shock Cord Attachment to Nose Cone
11.1 | Shroud line threading
11.1.1 | Thread shroud lines
11.2 | Parachute pass throough
11.2.1 | Pass parachute through loop
11.3 | Line tightening
11.3.1 | Pull lines tight
11.4 | Shock cord tie down
11.4.1 | Tie down shock cord free end
12.0 | Finishing Rocket
12.1 | Verify dryness
12.1.1 | Check to ensure glue joint are dry
12.2 | Prime rocket
12.2.1 | Apply primer coat #1
12.2.2 | Sand rocket body #1
12.2.3 | Apply primer coat #2
12.2.4 | Sand rocket body #2
12.3 | Paint rocket
12.3.1 | Insert paint handle
12.3.2 | Apply paint to rocket
12.3.3 | Allow to dry
12.4 | Apply Water Decals
12.4.1 | Cut decals
12.4.1.1 | Decal #1
12.4.1.2 | Decal #2
12.4.1.3 | Decal #3
12.4.1.4 | Decal #4
12.4.1.5 | Decal #5
12.4.1.6 | Decal #6
12.4.1.7 | Decal #7
12.4.1.8 | Decal #8
12.4.1.9 | Decal #9
12.4.1.10 | Decal #10
12.4.1.11 | Decal #11
12.4.1.12 | Decal #12
12.4.1.13 | Decal #13
12.4.2 | Dip in water
12.4.2.1 | Decal #1
12.4.2.2 | Decal #2
12.4.2.3 | Decal #3
12.4.2.4 | Decal #4
12.4.2.5 | Decal #5
12.4.2.6 | Decal #6
12.4.2.7 | Decal #7
12.4.2.8 | Decal #8
12.4.2.9 | Decal #9
12.4.2.10 | Decal #10
12.4.2.11 | Decal #11
12.4.2.12 | Decal #12
12.4.2.13 | Decal #13
12.4.3 | Slip decals
12.4.3.1 | Decal #1
12.4.3.2 | Decal #2
12.4.3.3 | Decal #3
12.4.3.4 | Decal #4
12.4.3.5 | Decal #5
12.4.3.6 | Decal #6
12.4.3.7 | Decal #7
12.4.3.8 | Decal #8
12.4.3.9 | Decal #9
12.4.3.10 | Decal #10
12.4.3.11 | Decal #11
12.4.3.12 | Decal #12
12.4.3.13 | Decal #13
12.4.4 | Blot decals
12.4.4.1 | Decal #1
12.4.4.2 | Decal #2
12.4.4.3 | Decal #3
12.4.4.4 | Decal #4
12.4.4.5 | Decal #5
12.4.4.6 | Decal #6
12.4.4.7 | Decal #7
12.4.4.8 | Decal #8
12.4.4.9 | Decal #9
12.4.4.10 | Decal #10
12.4.4.11 | Decal #11
12.4.4.12 | Decal #12
12.4.4.13 | Decal #13
12.4.5 | Dry decals
12.5.1 | Allow to dry overnight
12.4.6 | Apply clear spray to decals
12.4.1 | Apply spray to rocket
12.5 | Apply large decals
12.5.1 | Peel backing
12.5.2 | Cut away backing
12.5.3 | Align decal
12.5.4 | Peel off backing
12.5.5 | Smooth decal

## Rates
Place your roles and hourly rates here. Remove the example and replace with your project roles and rates.
Fitter | Draftsman | Cutter | Gluer | Painter | Sander | Sr Sander
9 | 35 | 12.25 | 8 | 11.5 | 7.5 | 13

## Roll-Up Est (hidden)
WBS # | TASKS | Fitter | Draftsman | Cutter | Gluer | Painter | Sander | Sr Sander | Dummy | Duration
1.0 | Engine Mount Assembly | 10 | 4 | 1 | 2 | 0 | 0 | 0 | 1 | 18
1.1 | Locate engine mount parts | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Locate light blue engine mount tube | 1
1.1.2 | Locate engine hook | 1
1.1.3 | Locate green adapter ring | 1
1.2 | Laying mount to ruler | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1 | Move tube to ruler | 1
1.2.2 | Align with zero mark | 1
1.3 | Marking mount | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1 | Take pencil |  | 1
1.3.2 | Mark tube | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1.3.2.1 | Mark 25mm |  | 1
1.3.2.2 | Mark 64 mm |  | 1
1.4 | Cutting mount | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
1.4.1 | Cut 3mm slit |  |  | 1
1.5 | Inserting hook | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5.1 | Insert hook | 1
1.5.2 | Extend hook | 1
1.6 | Testing adapter ring | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1.6.1 | Slide ring into front of engine tube | 1
1.6.2 | Slide ring over engine hook to 25mm mark | 1 | 1
1.7 | Glue & Dry | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 1
1.7.1 | Apply glue | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
1.7.1.1 | Apply glue to one side |  |  |  | 1
1.7.1.2 | Apply glue to other side |  |  |  | 1
1.7.2 | Dry glue | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
1.7.2.1 | Set assembly aside | 1
1.7.2.2 | Allow to dry | [7 empty] | 1
2.0 | Shock Cord Mount Assembly | 7 | 0 | 1 | 3 | 0 | 0 | 0 | 1 | 12
2.1 | Locate cord mount parts | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 | Locate cord mount on pattern sheet | 1
2.2 | Cut cord mount | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
2.2.1 | Cut cord mount along outline |  |  | 1
2.3 | Crease assembly | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1 | Fold on dotted lines | 1
2.3.2 | Crease on dotted lines | 1
2.4 | Glue mount assembly | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0
2.4.1 | Spread glue |  |  |  | 1
2.4.2 | Lay end of shock cord in glue | 1 |  |  | 1
2.5 | Fold mount assembly | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0
2.5.1 | Fold section 1 | 1
2.5.2 | Apply glue section 3 |  |  |  | 1
2.5.3 | Fold again | 1
2.6 | Clamp mount assembly | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2.6.1 | Clamp assembly | 1
2.6.2 | Allow to dry | [7 empty] | 1
3.0 | Fin Preparation | 6 | 6 | 7 | 0 | 0 | 2 | 9 | 0 | 30
3.1 | Select fin pattern | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
3.1.1 | Select fin pattern | 1
3.1.2 | Cut fin pattern from sheet |  |  | 1
3.2 | Trace fin patterns | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1 | Trace fin #1 |  | 1
3.2.2 | Match fin #1 | 1 | 1
3.2.3 | Trace fin #2 |  | 1
3.2.4 | Match fin #2 | 1 | 1
3.2.5 | Trace fin #2 |  | 1
3.2.6 | Match fin #2 | 1 | 1
3.3 | Cut fin patterns | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
3.3.1 | Cut fin #1 |  |  | 1
3.3.2 | Chect fin #1 |  |  | 1
3.3.3 | Cut fin #2 |  |  | 1
3.3.4 | Chect fin #2 |  |  | 1
3.3.5 | Cut fin #3 |  |  | 1
3.3.6 | Chect fin #3 |  |  | 1
3.4 | Save scrap | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.1 | Set aside piece scrap basa wood | 1
3.5 | Course sand fins | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
3.5.1 | Lay sandpaper | [5 empty] | 1
3.5.2 | Stack fins | 1
3.5.3 | Sand fins | [5 empty] | 1
3.6 | Fine sand fins | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0
3.6.1 | Fine sand fin #1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
3.6.1.1 | Round leading edge fin #1 | [6 empty] | 1
3.6.1.2 | Round trailing edge fin #1 | [6 empty] | 1
3.6.1.3 | Streamline training edge fin #1 | [6 empty] | 1
3.6.2 | Fine sand fin #2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
3.6.2.1 | Round leading edge fin #2 | [6 empty] | 1
3.6.2.2 | Round trailing edge fin #2 | [6 empty] | 1
3.6.2.3 | Streamline training edge fin #2 | [6 empty] | 1
3.6.3 | Fine sand fin #3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
3.6.3.1 | Round leading edge fin #3 | [6 empty] | 1
3.6.3.2 | Round trailing edge fin #3 | [6 empty] | 1
3.6.3.3 | Streamline training edge fin #3 | [6 empty] | 1
4.0 | Engine Mount Installation | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 4
4.1 | Locate body tube | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 | Locate body tube | 1
4.2 | Measure body tube | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
4.2.1 | Measure body tube 38 mm |  | 1
4.3 | Spread glue | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
4.3.1 | Spread glue around body tube |  |  |  | 1
4.4 | Insert engine mount | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1 | Insert engine mount assembly into body tube | 1
5.0 | Tube Marking Detail | 4 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 16
5.1 | Locate tube marking guide | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
5.1.1 | Locate tube marking guide on pattern sheet | 1
5.1.2 | Cut guide alone outline |  |  | 1
5.2 | Wrap guide | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.1 | Wrap guide around body tube | 1
5.2.2 | Tape guide to body tube | 1
5.3 | Mark tube | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1 | Mark tube for fins | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
5.3.1.1 | Mark tube for fin #1 |  | 1
5.3.1.2 | Mark tube for fin #2 |  | 1
5.3.1.3 | Mark tube for fin #3 |  | 1
5.3.2 | Write LL on body tube |  | 1
5.3.3 | Remove guide | 1
5.4 | Draw fin markings | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0
5.4.1 | Fin #1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
5.4.1.1 | Draw straight line |  | 1
5.4.1.2 | Extend line 76mm |  | 1
5.4.2 | Fin #2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
5.4.2.1 | Draw straight line |  | 1
5.4.2.2 | Extend line 76mm |  | 1
5.4.3 | Fin #3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
5.4.3.1 | Draw straight line |  | 1
5.4.3.2 | Extend line 76mm |  | 1
5.4.4 | Draw launch lug line | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
5.4.4.1 | Draw line 102 mm |  | 1
6.0 | Fin Attachment | 13 | 0 | 0 | 6 | 0 | 0 | 0 | 4 | 23
6.1 | Apply glue to root edges of fins | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
6.1.1 | Apply to fin #1 |  |  |  | 1
6.1.2 | Allow fin #1 to dry | [7 empty] | 1
6.1.3 | Apply to fin #2 |  |  |  | 1
6.1.4 | Allow fin #2 to dry | [7 empty] | 1
6.1.5 | Apply to fin #3 |  |  |  | 1
6.1.6 | Allow fin #3 to dry | [7 empty] | 1
6.2 | Apply second layer glue | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 0
6.2.1 | Apply more glue to Fin #1 |  |  |  | 1
6.2.2 | Set fin #1 | 1
6.2.3 | Press fin #1 | 1
6.2.4 | Apply more glue to Fin #2 |  |  |  | 1
6.2.5 | Set fin #2 | 1
6.2.6 | Press fin #2 | 1
6.2.7 | Apply more glue to Fin #3 |  |  |  | 1
6.2.8 | Set fin #3 | 1
6.2.9 | Press fin #3 | 1
6.3 | Adjust fins | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.3.1 | Adjust fin #1 | 1
6.3.2 | Attach fin #1 | 1
6.3.3 | Adjust fin #2 | 1
6.3.4 | Attach fin #2 | 1
6.3.5 | Adjust fin #3 | 1
6.3.6 | Attach fin #3 | 1
6.4 | Set aside to dry | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6.4.1 | Stand rocket on drying table | 1
6.4.2 | Allow fins to dry | [7 empty] | 1
7.0 | Launch Lug Attachment | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 1 | 6
7.1 | Measure lug attachement | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
7.1.1 | Measure 41mm |  | 1
7.1.2 | Mark attachment point |  | 1
7.2 | Glue lug attachment | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
7.2.1 | Apply glue to launch lug |  |  |  | 1
7.2.2 | Attach launch lug to body tube | 1
7.3 | Dry lug attachment | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
7.3.1 | Ensure launch lug alignment |  | 1
7.3.2 | Allow to dry | [7 empty] | 1
8.0 | Glue Reinforcement | 1 | 0 | 0 | 6 | 0 | 0 | 0 | 1 | 8
8.1 | Reinforce fins | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
8.1.1 | Reinforce fin fin #1 |  |  |  | 1
8.1.2 | Reinforce fin fin #2 |  |  |  | 1
8.1.3 | Reinforce fin fin #3 |  |  |  | 1
8.2 | Reinforce launch lug | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
8.2.1 | Reinforch side 1 |  |  |  | 1
8.2.2 | Reinforce side 2 |  |  |  | 1
8.3 | Glue drying | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
8.3.1 | Stand rocket on drying table | 1
8.3.2 | Wipe away excess glue |  |  |  | 1
8.3.3 | Allow to dry | [7 empty] | 1
9.0 | Shock Cord Mount Attachment | 4 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 8
9.1 | Measure body tube | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
9.1.1 | Measure 25mm |  | 1
9.2 | Apply glue | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
9.2.1 | Apply glue to shock cord |  |  |  | 1
9.2.2 | Insert cord into tube | 1
9.3 | Set mount | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0
9.3.1 | Set mount 25mm | 1
9.3.2 | Press mount into glue | 1 |  |  | 1
9.4 | Set glue | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
9.4.1 | Hold mount attachment | 1
9.4.2 | Allow to dry | [7 empty] | 1
10.0 | Parachute Assembly | 15 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 23
10.1 | Cut out parachute | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
10.1.1 | Cut parachute along line |  |  | 1
10.2 | Tape removal | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
10.2.1 | Remove tape | 1
10.2.2 | Fold shroud lines | 1
10.2.3 | Cut shroud lines |  |  | 1
10.3 | Tape attachment | 12 | 0 | 6 | 0 | 0 | 0 | 0 | 0
10.3.1 | Attach tape rings | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.3.1.1 | Attach tape ring #1 | 1
10.3.1.2 | Attach tape ring #2 | 1
10.3.1.3 | Attach tape ring #3 | 1
10.3.1.4 | Attach tape ring #4 | 1
10.3.1.5 | Attach tape ring #5 | 1
10.3.1.6 | Attach tape ring #6 | 1
10.3.2 | Press tape tape rings into place | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.3.2.1 | Press tape tape rings into place #1 | 1
10.3.2.2 | Press tape tape rings into place #2 | 1
10.3.2.3 | Press tape tape rings into place #3 | 1
10.3.2.4 | Press tape tape rings into place #4 | 1
10.3.2.5 | Press tape tape rings into place #5 | 1
10.3.2.6 | Press tape tape rings into place #6 | 1
10.3.3 | Punch tape ring holes | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
10.3.3.1 | Punch tape ring holes #1 |  |  | 1
10.3.3.2 | Punch tape ring holes #2 |  |  | 1
10.3.3.3 | Punch tape ring holes #3 |  |  | 1
10.3.3.4 | Punch tape ring holes #4 |  |  | 1
10.3.3.5 | Punch tape ring holes #5 |  |  | 1
10.3.3.6 | Punch tape ring holes #6 |  |  | 1
10.4 | Shroud line assembly | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.4.1 | Pass shroud line through hole | 1
10.4.2 | Tie lines together
11.0 | Parachute & Shock Cord Attachment to Nose Cone | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
11.1 | Shroud line threading | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.1.1 | Thread shroud lines | 1
11.2 | Parachute pass throough | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.2.1 | Pass parachute through loop | 1
11.3 | Line tightening | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.3.1 | Pull lines tight | 1
11.4 | Shock cord tie down | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.4.1 | Tie down shock cord free end | 1
12.0 | Finishing Rocket | 45 | 1 | 14 | 1 | 4 | 0 | 2 | 9 | 76
12.1 | Verify dryness | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
12.1.1 | Check to ensure glue joint are dry |  |  |  | 1
12.2 | Prime rocket | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0
12.2.1 | Apply primer coat #1 |  |  |  |  | 1
12.2.2 | Sand rocket body #1 | [6 empty] | 1
12.2.3 | Apply primer coat #2 |  |  |  |  | 1
12.2.4 | Sand rocket body #2 | [6 empty] | 1
12.3 | Paint rocket | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1
12.3.1 | Insert paint handle | 1
12.3.2 | Apply paint to rocket |  |  |  |  | 1
12.3.3 | Allow to dry | [7 empty] | 1
12.4 | Apply Water Decals | 39 | 0 | 13 | 0 | 1 | 0 | 0 | 8
12.4.1 | Cut decals | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0
12.4.1.1 | Decal #1 |  |  | 1
12.4.1.2 | Decal #2 |  |  | 1
12.4.1.3 | Decal #3 |  |  | 1
12.4.1.4 | Decal #4 |  |  | 1
12.4.1.5 | Decal #5 |  |  | 1
12.4.1.6 | Decal #6 |  |  | 1
12.4.1.7 | Decal #7 |  |  | 1
12.4.1.8 | Decal #8 |  |  | 1
12.4.1.9 | Decal #9 |  |  | 1
12.4.1.10 | Decal #10 |  |  | 1
12.4.1.11 | Decal #11 |  |  | 1
12.4.1.12 | Decal #12 |  |  | 1
12.4.1.13 | Decal #13 |  |  | 1
12.4.2 | Dip in water | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.4.2.1 | Decal #1 | 1
12.4.2.2 | Decal #2 | 1
12.4.2.3 | Decal #3 | 1
12.4.2.4 | Decal #4 | 1
12.4.2.5 | Decal #5 | 1
12.4.2.6 | Decal #6 | 1
12.4.2.7 | Decal #7 | 1
12.4.2.8 | Decal #8 | 1
12.4.2.9 | Decal #9 | 1
12.4.2.10 | Decal #10 | 1
12.4.2.11 | Decal #11 | 1
12.4.2.12 | Decal #12 | 1
12.4.2.13 | Decal #13 | 1
12.4.3 | Slip decals | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.4.3.1 | Decal #1 | 1
12.4.3.2 | Decal #2 | 1
12.4.3.3 | Decal #3 | 1
12.4.3.4 | Decal #4 | 1
12.4.3.5 | Decal #5 | 1
12.4.3.6 | Decal #6 | 1
12.4.3.7 | Decal #7 | 1
12.4.3.8 | Decal #8 | 1
12.4.3.9 | Decal #9 | 1
12.4.3.10 | Decal #10 | 1
12.4.3.11 | Decal #11 | 1
12.4.3.12 | Decal #12 | 1
12.4.3.13 | Decal #13 | 1
12.4.4 | Blot decals | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.4.4.1 | Decal #1 | 1
12.4.4.2 | Decal #2 | 1
12.4.4.3 | Decal #3 | 1
12.4.4.4 | Decal #4 | 1
12.4.4.5 | Decal #5 | 1
12.4.4.6 | Decal #6 | 1
12.4.4.7 | Decal #7 | 1
12.4.4.8 | Decal #8 | 1
12.4.4.9 | Decal #9 | 1
12.4.4.10 | Decal #10 | 1
12.4.4.11 | Decal #11 | 1
12.4.4.12 | Decal #12 | 1
12.4.4.13 | Decal #13 | 1
12.4.5 | Dry decals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
12.5.1 | Allow to dry overnight | [7 empty] | 8
12.4.6 | Apply clear spray to decals | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
12.4.1 | Apply spray to rocket |  |  |  |  | 1
12.5 | Apply large decals | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0
12.5.1 | Peel backing | 1
12.5.2 | Cut away backing |  |  | 1
12.5.3 | Align decal |  | 1
12.5.4 | Peel off backing | 1
12.5.5 | Smooth decal | 1
| RESOURCE TOTALS | 112 | 27 | 32 | 22 | 4 | 2 | 11 | 18 | 228 | TOTAL DURATION ESTIMATE
| RESOURCE RATES | 9 | 35 | 12.25 | 8 | 11.5 | 7.5 | 13
| RESOURCE COSTS | 1008 | 945 | 392 | 176 | 46 | 15 | 143 | 0 | 2725 | TOTAL RESOURCE COST

## M&E List (hidden)
WBS # | WBS Task | Ball Point Pen | Scissors | Tube Marking Guide | Knife | Ruler | Glue | Sandpaper | Masking Tape | Enamel Spray Paint | Sanding Primer | Pencil | Parachute | Shroud Lines | Engine Hook
1.0 | Engine Mount Assembly
2.0 | Shock Cord Mount Assembly
3.0 | Fin Preparation
4.0 | Engine Mount Installation
5.0 | Tube Marking Detail
6.0 | Fin Attachment
7.0 | Launch Lug Attachment
8.0 | Glue Reinforcement
9.0 | Shock Cord Mount Attachment
10.0 | Parachute Assembly
11.0 | Parachute & Shock Cord Attachment to Nose Cone
12.0 | Finishing Rocket

## M&E Forecast (hidden)
WBS # | TASKS | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19
1.0 | Engine Mount Assembly
1.1 | Locate engine mount parts
1.1.1 | Locate light blue engine mount tube
1.1.2 | Locate engine hook
1.1.3 | Locate green adapter ring
1.2 | Laying mount to ruler | Ruler
1.2.1 | Move tube to ruler
1.2.2 | Align with zero mark
1.3 | Marking mount | Pencil
1.3.1 | Take pencil
1.3.2 | Mark tube | Tube Marking Guide
1.3.2.1 | Mark 25mm
1.3.2.2 | Mark 64 mm
1.4 | Cutting mount |  | Knife
1.4.1 | Cut 3mm slit
1.5 | Inserting hook
1.5.1 | Insert hook
1.5.2 | Extend hook
1.6 | Testing adapter ring
1.6.1 | Slide ring into front of engine tube
1.6.2 | Slide ring over engine hook to 25mm mark
1.7 | Glue & Dry
1.7.1 | Apply glue |  | Glue
1.7.1.1 | Apply glue to one side
1.7.1.2 | Apply glue to other side
1.7.2 | Dry glue
1.7.2.1 | Set assembly aside
1.7.2.2 | Allow to dry
2.0 | Shock Cord Mount Assembly
2.1 | Locate cord mount parts
2.1.1 | Locate cord mount on pattern sheet
2.2 | Cut cord mount | Scissors
2.2.1 | Cut cord mount along outline
2.3 | Crease assembly
2.3.1 | Fold on dotted lines
2.3.2 | Crease on dotted lines
2.4 | Glue mount assembly | Glue
2.4.1 | Spread glue
2.4.2 | Lay end of shock cord in glue
2.5 | Fold mount assembly
2.5.1 | Fold section 1
2.5.2 | Apply glue section 3 |  | Glue
2.5.3 | Fold again
2.6 | Clamp mount assembly
2.6.1 | Clamp assembly
2.6.2 | Allow to dry
3.0 | Fin Preparation
3.1 | Select fin pattern
3.1.1 | Select fin pattern
3.1.2 | Cut fin pattern from sheet | Scissors
3.2 | Trace fin patterns | Pencil
3.2.1 | Trace fin #1
3.2.2 | Match fin #1
3.2.3 | Trace fin #2
3.2.4 | Match fin #2
3.2.5 | Trace fin #2
3.2.6 | Match fin #2
3.3 | Cut fin patterns | Scissors
3.3.1 | Cut fin #1
3.3.2 | Chect fin #1
3.3.3 | Cut fin #2
3.3.4 | Chect fin #2
3.3.5 | Cut fin #3
3.3.6 | Chect fin #3
3.4 | Save scrap
3.4.1 | Set aside piece scrap basa wood
3.5 | Course sand fins | Sandpaper
3.5.1 | Lay sandpaper
3.5.2 | Stack fins
3.5.3 | Sand fins
3.6 | Fine sand fins |  | Sandpaper | Sandpaper
3.6.1 | Fine sand fin #1
3.6.1.1 | Round leading edge fin #1
3.6.1.2 | Round trailing edge fin #1
3.6.1.3 | Streamline training edge fin #1
3.6.2 | Fine sand fin #2
3.6.2.1 | Round leading edge fin #2
3.6.2.2 | Round trailing edge fin #2
3.6.2.3 | Streamline training edge fin #2
3.6.3 | Fine sand fin #3
3.6.3.1 | Round leading edge fin #3
3.6.3.2 | Round trailing edge fin #3
3.6.3.3 | Streamline training edge fin #3
4.0 | Engine Mount Installation
4.1 | Locate body tube
4.1.1 | Locate body tube
4.2 | Measure body tube |  |  | Ruler
4.2.1 | Measure body tube 38 mm
4.3 | Spread glue |  |  | Glue
4.3.1 | Spread glue around body tube
4.4 | Insert engine mount
4.4.1 | Insert engine mount assembly into body tube
5.0 | Tube Marking Detail
5.1 | Locate tube marking guide
5.1.1 | Locate tube marking guide on pattern sheet
5.1.2 | Cut guide alone outline |  |  |  | Scissors
5.2 | Wrap guide |  |  |  | Masking Tape
5.2.1 | Wrap guide around body tube
5.2.2 | Tape guide to body tube
5.3 | Mark tube |  |  |  | Pencil
5.3.1 | Mark tube for fins
5.3.1.1 | Mark tube for fin #1
5.3.1.2 | Mark tube for fin #2
5.3.1.3 | Mark tube for fin #3
5.3.2 | Write LL on body tube |  |  |  |  | Ball Point Pen
5.3.3 | Remove guide
5.4 | Draw fin markings |  |  |  |  | Pencil
5.4.1 | Fin #1 |  |  |  |  | Ruler
5.4.1.1 | Draw straight line
5.4.1.2 | Extend line 76mm
5.4.2 | Fin #2
5.4.2.1 | Draw straight line
5.4.2.2 | Extend line 76mm
5.4.3 | Fin #3
5.4.3.1 | Draw straight line
5.4.3.2 | Extend line 76mm
5.4.4 | Draw launch lug line | [5 empty] | Pencil
5.4.4.1 | Draw line 102 mm | [5 empty] | Ruler
6.0 | Fin Attachment
6.1 | Apply glue to root edges of fins | [5 empty] | Glue
6.1.1 | Apply to fin #1
6.1.2 | Allow fin #1 to dry
6.1.3 | Apply to fin #2
6.1.4 | Allow fin #2 to dry
6.1.5 | Apply to fin #3
6.1.6 | Allow fin #3 to dry
6.2 | Apply second layer glue | [6 empty] | Glue
6.2.1 | Apply more glue to Fin #1
6.2.2 | Set fin #1
6.2.3 | Press fin #1
6.2.4 | Apply more glue to Fin #2
6.2.5 | Set fin #2
6.2.6 | Press fin #2
6.2.7 | Apply more glue to Fin #3
6.2.8 | Set fin #3
6.2.9 | Press fin #3
6.3 | Adjust fins
6.3.1 | Adjust fin #1
6.3.2 | Attach fin #1
6.3.3 | Adjust fin #2
6.3.4 | Attach fin #2
6.3.5 | Adjust fin #3
6.3.6 | Attach fin #3
6.4 | Set aside to dry
6.4.1 | Stand rocket on drying table
6.4.2 | Allow fins to dry
7.0 | Launch Lug Attachment
7.1 | Measure lug attachement | [8 empty] | Ruler
7.1.1 | Measure 41mm
7.1.2 | Mark attachment point | [8 empty] | Pencil
7.2 | Glue lug attachment | [8 empty] | Glue
7.2.1 | Apply glue to launch lug
7.2.2 | Attach launch lug to body tube
7.3 | Dry lug attachment
7.3.1 | Ensure launch lug alignment
7.3.2 | Allow to dry
8.0 | Glue Reinforcement | [9 empty] | Glue
8.1 | Reinforce fins
8.1.1 | Reinforce fin fin #1
8.1.2 | Reinforce fin fin #2
8.1.3 | Reinforce fin fin #3
8.2 | Reinforce launch lug
8.2.1 | Reinforch side 1
8.2.2 | Reinforce side 2
8.3 | Glue drying
8.3.1 | Stand rocket on drying table
8.3.2 | Wipe away excess glue
8.3.3 | Allow to dry
9.0 | Shock Cord Mount Attachment
9.1 | Measure body tube |  |  |  | Ruler
9.1.1 | Measure 25mm
9.2 | Apply glue |  |  |  | Glue
9.2.1 | Apply glue to shock cord
9.2.2 | Insert cord into tube
9.3 | Set mount
9.3.1 | Set mount 25mm
9.3.2 | Press mount into glue
9.4 | Set glue |  |  |  |  | Glue
9.4.1 | Hold mount attachment
9.4.2 | Allow to dry
10.0 | Parachute Assembly
10.1 | Cut out parachute | Sissors
10.1.1 | Cut parachute along line
10.2 | Tape removal
10.2.1 | Remove tape
10.2.2 | Fold shroud lines
10.2.3 | Cut shroud lines | Knife
10.3 | Tape attachment |  | Masking Tape
10.3.1 | Attach tape rings
10.3.1.1 | Attach tape ring #1
10.3.1.2 | Attach tape ring #2
10.3.1.3 | Attach tape ring #3
10.3.1.4 | Attach tape ring #4
10.3.1.5 | Attach tape ring #5
10.3.1.6 | Attach tape ring #6
10.3.2 | Press tape tape rings into place
10.3.2.1 | Press tape tape rings into place #1
10.3.2.2 | Press tape tape rings into place #2
10.3.2.3 | Press tape tape rings into place #3
10.3.2.4 | Press tape tape rings into place #4
10.3.2.5 | Press tape tape rings into place #5
10.3.2.6 | Press tape tape rings into place #6
10.3.3 | Punch tape ring holes
10.3.3.1 | Punch tape ring holes #1
10.3.3.2 | Punch tape ring holes #2
10.3.3.3 | Punch tape ring holes #3
10.3.3.4 | Punch tape ring holes #4
10.3.3.5 | Punch tape ring holes #5
10.3.3.6 | Punch tape ring holes #6
10.4 | Shroud line assembly |  |  | Shroud Lines
10.4.1 | Pass shroud line through hole
10.4.2 | Tie lines together
11.0 | Parachute & Shock Cord Attachment to Nose Cone
11.1 | Shroud line threading
11.1.1 | Thread shroud lines
11.2 | Parachute pass throough
11.2.1 | Pass parachute through loop
11.3 | Line tightening
11.3.1 | Pull lines tight
11.4 | Shock cord tie down
11.4.1 | Tie down shock cord free end
12.0 | Finishing Rocket
12.1 | Verify dryness
12.1.1 | Check to ensure glue joint are dry
12.2 | Prime rocket | Sanding Primer
12.2.1 | Apply primer coat #1
12.2.2 | Sand rocket body #1
12.2.3 | Apply primer coat #2
12.2.4 | Sand rocket body #2
12.3 | Paint rocket |  |  | Enamel Spray Paint
12.3.1 | Insert paint handle
12.3.2 | Apply paint to rocket
12.3.3 | Allow to dry
12.4 | Apply Water Decals
12.4.1 | Cut decals | [9 empty] | Sissors
12.4.1.1 | Decal #1
12.4.1.2 | Decal #2
12.4.1.3 | Decal #3
12.4.1.4 | Decal #4
12.4.1.5 | Decal #5
12.4.1.6 | Decal #6
12.4.1.7 | Decal #7
12.4.1.8 | Decal #8
12.4.1.9 | Decal #9
12.4.1.10 | Decal #10
12.4.1.11 | Decal #11
12.4.1.12 | Decal #12
12.4.1.13 | Decal #13
12.4.2 | Dip in water
12.4.2.1 | Decal #1
12.4.2.2 | Decal #2
12.4.2.3 | Decal #3
12.4.2.4 | Decal #4
12.4.2.5 | Decal #5
12.4.2.6 | Decal #6
12.4.2.7 | Decal #7
12.4.2.8 | Decal #8
12.4.2.9 | Decal #9
12.4.2.10 | Decal #10
12.4.2.11 | Decal #11
12.4.2.12 | Decal #12
12.4.2.13 | Decal #13
12.4.3 | Slip decals
12.4.3.1 | Decal #1
12.4.3.2 | Decal #2
12.4.3.3 | Decal #3
12.4.3.4 | Decal #4
12.4.3.5 | Decal #5
12.4.3.6 | Decal #6
12.4.3.7 | Decal #7
12.4.3.8 | Decal #8
12.4.3.9 | Decal #9
12.4.3.10 | Decal #10
12.4.3.11 | Decal #11
12.4.3.12 | Decal #12
12.4.3.13 | Decal #13
12.4.4 | Blot decals
12.4.4.1 | Decal #1
12.4.4.2 | Decal #2
12.4.4.3 | Decal #3
12.4.4.4 | Decal #4
12.4.4.5 | Decal #5
12.4.4.6 | Decal #6
12.4.4.7 | Decal #7
12.4.4.8 | Decal #8
12.4.4.9 | Decal #9
12.4.4.10 | Decal #10
12.4.4.11 | Decal #11
12.4.4.12 | Decal #12
12.4.4.13 | Decal #13
12.4.5 | Dry decals
12.5.1 | Allow to dry overnight
12.4.6 | Apply clear spray to decals | [14 empty] | Enamel Spray Paint
12.4.1 | Apply spray to rocket
12.5 | Apply large decals
12.5.1 | Peel backing
12.5.2 | Cut away backing | [15 empty] | Sissors
12.5.3 | Align decal | [15 empty] | Knife
12.5.4 | Peel off backing
12.5.5 | Smooth decal