## User-StoriesProduct Backlog
ID | Theme | As a/an | I want to | so that | Notes | PRODUCT BACKLOG |  |  |  | SPRINT TASKS
[6 empty] | Priority | Status | Tasks # | Tasks | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
1 | Development | Developer | use GitHub | source control is easier for collaborating with the team |  |  |  | 8 |  | 2023-08-08
[6 empty] | 1 | Completed | Task1 | Create a Github repository
[6 empty] | 3 | Completed | Task3 | Create Visual Studio Solution and Project
2 | Development | Developer | create a database | the program can store data
[6 empty] | 2 | Completed | Task2 | Design Database
[6 empty] | 4 | Completed | Task4 | Create database tables for book info
[6 empty] | 5 | Completed | Task5 | Create database tables for library info and combining tables
[6 empty] | 6 | Completed | Task6 | Create database roles
[6 empty] | 7 | Completed | Task7 | Create dummy data
[6 empty] | 8 | Completed | Task18 | Testing database
3 | Functional | User | Be able to see my account | I know how many books I have checked out, how much in fines I owe, and when to return a book so that I'm not fined for overdue books |  |  |  | 7 |  |  | 0/7
[6 empty] | 9 | Not Started | Task8 | Create account view page
[6 empty] | 10 | Not Started | Task9 | Create login page
[6 empty] | 11 | Not Started | Task10 | Connect UI to database
8 | Functional | User | search for a certain topic | I can do research.
[6 empty] | 12 | Not Started | Task11 | Add UI page for querying books
7 | Functional | User | see which library a book is in | I can borrow it.
[6 empty] | 13 | Not Started | Task12 | Add UI page for viewing books
[6 empty] | 14 | Not Started | Task13 | Connect UI to database
4 | Functional | Librarian | be able to add or remove books from the catalog | the system is kept up to date
[6 empty] | 15 | Not Started | Task14 | Add UI page for CRUD functions
5 | Functional | Librarian | The system to limit the amount of books users can check out | they don't check out too many |  |  |  | 7 |  |  |  | 0/7
[6 empty] | 16 | Not Started | Task15 | Develop Automated systems
6 | Functional | Librarian | The system to prevent people from getting new books if their books are overdue | they can't check out more books while they owe a fine
[6 empty] | 17 | Not Started | Task16 | Develop automated systems
9 | Functional | User | I want to see detailed information about a book, including its summary, author details, and availability status | I can make an informed decisions about borrowing it
[6 empty] | 19 | Not Started | Task 19 | Add summary, author details, and availability
10 | Functional | User | I want to have the option to save books to a wishlist for future reading | it is easier to keep track of books I am interested in
[6 empty] | 20 | Not Started | Task 20 | Add wishlist
11 | Functional | User | I want the app to provide information about upcoming library events, such as author talks, book clubs, and workshops | I can participate in community activities
[6 empty] | 21 | Not Started | Task 21 | Add event page
12 | Functional | User | I want the app to have a feature that suggests books based on the current weather or season | it creates a curated reading experience.
[6 empty] | 22 | Not Started | Task 22 | Add book suggestions
13 | Functional | User | I want the ability to create and share reading lists with other members | fosters a sense of community and facilitates collaborative reading.
[6 empty] | 23 | Not Started | Task 23 | Add reading list creation and sharing
7 | Development | Developer | Make sure the application works properly | The end user has a good experience |  |  |  | 4 |  |  |  |  | 0/4
[6 empty] | 18 | Not Started | Task17 | Testing Login
[6 empty] | 24 | Not Started | Task24 | Testing Account Page
[6 empty] | 25 | Not Started | Task25 | Testing Library catalog
[6 empty] | 26 | Not Started | Task26 | Testing UI

## Product Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2023-11-22 | 26 | 26 | Bold = completed.
Thu | 2023-11-23 | 25 | 25
Fri | 2023-11-24 | 24 | 25
Sat | 2023-11-25 | 24 | 24
Sun | 2023-11-26 | 24 | 24
Mon | 2023-11-27 | 24 | 24
Tue | 2023-11-28 | 23 | 24
Wed | 2023-11-29 | 23 | 24
Thu | 2023-11-30 | 23 | 24
Fri | 2023-12-01 | 23 | 23
Sat | 2023-12-02 | 22 | 23
Sun | 2023-12-03 | 21 | 20
Mon | 2023-12-04 | 20 | 18
Tue | 2023-12-05 | 19 | 18
Wed | 2023-12-06 | 18
Thu | 2023-12-07 | 18
Fri | 2023-12-08 | 17
Sat | 2023-12-09 | 17
Sun | 2023-12-10 | 17
Mon | 2023-12-11 | 16
Tue | 2023-12-12 | 16
Wed | 2023-12-13 | 16
Thu | 2023-12-14 | 15
Fri | 2023-12-15 | 14
Sat | 2023-12-16 | 14
Sun | 2023-12-17 | 13
Mon | 2023-12-18 | 12
Tue | 2023-12-19 | 12
Wed | 2023-12-20 | 11
Thu | 2023-12-21 | 11
Fri | 2023-12-22 | 10
Sat | 2023-12-23 | 10
Sun | 2023-12-24 | 10
Mon | 2023-12-25 | 9
Tue | 2023-12-26 | 9
Wed | 2023-01-03 | 8
Thu | 2023-01-04 | 8
Fri | 2023-01-05 | 7
Sat | 2023-01-06 | 7
Sun | 2023-01-07 | 6
Mon | 2023-01-08 | 6
Tue | 2023-01-09 | 5
Wed | 2023-01-10 | 4
Thu | 2023-01-11 | 4
Fri | 2023-01-12 | 3
Sat | 2023-01-13 | 3
Sun | 2023-01-14 | 2
Mon | 2023-01-15 | 2
Tue | 2023-01-16 | 1

## Sprint 1 Planning Backlog
User Story | Tasks | Team Member | Hours Estimated | Hours Actual | Notes
As a developer, I want to use GitHub so that source control is easier for collaborating with the team | Create a Github repository | Jesus | 1 | 1
| Create Visual Studio Solution and Project | Jesus | 1 | 1
As a developer, I want to create a database so that the program can store data | Design Database | Justin | 5 | 5
| Create dummy data | Jesus | 1 | 1
| Create database roles | Desmond | 1 | 1.5
| Create database tables for book info | Jesus | 2 | 3
| Create database tables for library info and combining tables | Desmond | 4 | 4.5 | Zig helped for 2 hours.
| Testing database | All | 2 | 2 | Everyone contributed 2 hours.
n/a | Scrum Master tasks | Zigmund | 8 | 10 | Includes preparing meetings, organizing, and editing transcripts.
n/a | Product Owner tasks | Sarah | 4 | 4
|  | Total | 29 | 33
|  | Hours/person | 2023-04-05

## Sprint 1 Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2023-11-22 | 8 | 8
Thurs | 2023-11-23 | 7 | 7
Fri | 2023-11-24 | 6 | 7
Sat | 2023-11-25 | 6 | 6
Sun | 2023-11-26 | 5 | 6
Mon | 2023-11-27 | 5 | 6
Tues | 2023-11-28 | 4 | 6
Wed | 2023-11-29 | 4 | 6
Thurs | 2023-11-30 | 4 | 6
Fri | 2023-12-01 | 4 | 5
Sat | 2023-12-02 | 3 | 5
Sun | 2023-12-03 | 3 | 2
Mon | 2023-12-04 | 2 | 0
Tues | 2023-12-05 | 1 | 0
Bold = completed
Mid-Sprint
Velocity
Seven tasks completed, one to go.
Testing
All two tasks passed testing.
Screenshots
Code
https://github.com/JesusHernandez25/TomeTender

## Sprint 1 Demo
Task | By | Accepted | Notes
Create a Github repository | Jesus | Yes
Create Visual Studio Solution and Project | Jesus | Yes
Design Database | Justin | Yes
Create dummy data | Jesus | Yes
Create database roles | Desmond | Yes
Create database tables for book info | Jesus | Yes
Create database tables for library info and combining tables | Desmond | Yes
Testing database | All | Yes
Product owner accepts |  | Yes
Demo screenshots here

## Sprint 1 Review
Done | Updated | Notes
2023-12-04 | Product backlog updated for new design concepts | None
PO satisifed with demo and sprint 1
End-Sprint
Velocity consisted of 8 tasks assigned and 8 tasks completed. No adjustments needed. |  |  | Tasks Assigned | Tasks Completed
|  |  | 8 | 8
Testing
All eight completed tasks passed testing.
Code
Completed | https://github.com/JesusHernandez25/TomeTender
Working
Review of sprint and product
Screenshots
SQL Code running
Database Diagram

## Sprint 1 Retrospective
What went well? | Improvements? | How?
As a team, doing a good job participating in meetings | Could be more knowledgeable in our collaboration tools | Do more research, learn how to use collaboration tools
Good at communicating, tell each other problems and help solve them | Could get better at informing team of updates | Use Discord and other tools more
Quick at getting work done once started |  | Check in with team members more
What can be done better in terms of process and not product here