## Source of Project Cost
Source of Project Cost
| PROJECT TASKS | LABOR HOURS | LABOR COST ($) | MATERIAL COST ($) | TRAVEL COST ($) | OTHER COST ($) | TOTAL PER TASK
PROJECT DESIGN | Develop Functional Specifications | 3 | 32.5 | 250 | 0 | 0 | 347.5
| Develop System Architecture | 7 | 32.5 | 400 | 0 | 0 | 627.5
| Develop Preliminary Design Specification | 4 | 32.5 | 150 | 1 | 1 | 282
| Develop Detailed Design Specifications | 4 | 32.5 | 200 | 1 | 1 | 332
| Develop Acceptance Test Plan | 2 | 32.5 | 150 | 1 | 1 | 217
| Subtotal | 20 | 162.5 | 1150 | 3 | 3 | 1806
PROJECT DEVELOPMENT | Develop Components | 4 | 25 | 300 | 0 | 0 | 400
| Procure Software | 4 | 25 | 250 | 0 | 0 | 350
| Procure Hardware | 1.5 | 25 | 175 | 0 | 0 | 212.5
| Development Acceptance Test Package | 2 | 25 | 150 | 0 | 0 | 200
| Perform Unit/Integration Test | 2.5 | 25 | 150 | 0 | 0 | 212.5
| Subtotal | 14 | 125 | 1025 | 0 | 0 | 1375
PROJECT DELIVERY | Install System | 3 | 35 | 750 | 0 | 0 | 855
| Train Customers | 1 | 35 | 250 | 0 | 0 | 285
| Perform Acceptance Test | 1.5 | 35 | 150 | 0 | 0 | 202.5
| Perform Post Project Review | 3 | 35 | 150 | 0 | 0 | 255
| Provide Warranty Support | 3 | 35 | 250 | 0 | 0 | 355
| Archive Materials | 4 | 35 | 1000 | 0 | 0 | 1140
| Subtotal | 15.5 | 210 | 2550 | 0 | 0 | 2237.5
PROJECT MANAGEMENT | Customer Progress Meetings/Reports | 2 | 28 | 200 | 0 | 0 | 256
| Internal Status Meetings/Reports | 1.5 | 28 | 150 | 0 | 0 | 192
| Third-Party Vendor Interface | 1.5 | 28 | 400 | 0 | 0 | 442
| Interface to Other Internal Departments | 2 | 28 | 350 | 0 | 0 | 406
| Configuration Management | 8 | 28 | 500 | 0 | 0 | 724
| Quality Assurance | 5 | 28 | 400 | 0 | 0 | 540
| Overall Project Management | 10 | 28 | 1000 | 0 | 0 | 1280
| Subtotal | 30 | 196 | 3000 | 0 | 0 | 3392
OTHER COST | Other cost | 0 | 0 | 0 | 0 | 0 | 0
| Other cost | 0 | 0 | 0 | 0 | 0 | 0
| Other cost | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 3392
Subtotals |  | 0 | 0 | 7725 | 3 | 3 | 12202.5
Risk (Contingency) |  | 0 | 0 | 0 | 0 | 0 | 0
Total (Scheduled) |  | 0 | 0 | 7725 | 3 | 3 | 12202.5

## Expenditures Over Time
Expenditures Over Time
|  | ITEM | COST | DATE | REASON FOR EXPENDITURE
| INSTALLATION | Install System | 875 | 2022-09-27
|  | Train Customers | 350 | 2022-09-27
|  | Perform Acceptance Test | 200 | 2022-09-29
|  | Perform Post Project Review | 150 | 2022-09-29
|  | Provide Warranty Support | 250 | 2022-09-29
|  | Achieve Materials | 1000 | 2022-09-29
|  | Subtotal | 2825
| PLANNING (RFP) | Install System | 750 | 2022-10-05
|  | Train Customers | 250 | 2022-10-06
|  | Perform Acceptance Test | 150 | 2022-10-07
|  | Perform Post Project Review | 150 | 2022-10-08
|  | Provide Warranty Support | 250 | 2022-10-09
|  | Achieve Materials | 1000 | 2022-10-10
|  | Subtotal | 2550
| PLANNING 2 | Install System | 750 | 2022-10-15
|  | Train Customers | 250 | 2022-10-16
|  | Perform Acceptance Test | 150 | 2022-10-17
|  | Perform Post Project Review | 150 | 2022-10-18
|  | Provide Warranty Support | 250 | 2022-10-19
|  | Achieve Materials | 1000 | 2022-10-20
|  | Subtotal | 2550
| CONSTRUCTION | Install System | 750 | 2022-10-22
|  | Train Customers | 250 | 2022-10-23
|  | Perform Acceptance Test | 150 | 2022-10-24
|  | Perform Post Project Review | 150 | 2022-10-25
|  | Provide Warranty Support | 250 | 2022-10-26
|  | Achieve Materials | 1000 | 2022-10-27
|  | Subtotal | 2550
| TEST & DELIVERY | Install System | 750 | 2022-11-02
|  | Train Customers | 250 | 2022-11-03
|  | Perform Acceptance Test | 150 | 2022-11-04
|  | Perform Post Project Review | 150 | 2022-11-05
|  | Provide Warranty Support | 250 | 2022-11-06
|  | Achieve Materials | 1000 | 2022-11-07
|  | Subtotal | 2550
| PROJECT TOTAL |  | 13025

## Cumulative Project Costs
Projected vs. Actual Costs
MONTHLY COST
CUMULATIVE COST

## Data Worksheet
Project Data Worksheet
| MONTH | PROJECTED MONTHLY COST | ACTUAL MONTHLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST
| 1 | 4100 | 3200 | 3500 | 4000
| 2 | 4100 | 2500 | 3200 | 3000
| 3 | 4100 | 6500 | 5500 | 5200